| Sept | Host team & administrator confirmed Venue booked |
| --- | --- |
| Oct | Brochure entry 1st host mtg |
| Nov | Worship Leader & Speaker confirmed |
| Dec |  |
| Jan | 2nd host mtg Reminder letter to last yr’s guests |
| Feb | Youth team leaders confirmed & contacted by host contact. Start gathering helpers |
| March | 3rd host mtg Mtg with Venue – contract agreed, deposit paid |
| April | Menus confirmed |
| May | List of helpers submitted to Safeguarding Admin Assistant for screening |
| June | 4th host mtg Bedrooms allocated (in time for July mailout) Youth leaders contacted by hosts – check ok, prayer / logistical requests Email to guests with early info – barbecue/fancy dress theme/Data permission for address list/balance to pay |
| July | Mailout to all guests * All deposits collected Final numbers & room lists to Venue (10 days before party) Discussion groups sorted Final host mtg (prayer) Welcome folders prepared ** Money balanced |
| Aug | Houseparty Post-houseparty report to ST including admin fees Bank balance settled / finances written up Access to talks shared/Thank yous sent |

* July mailout includes:

Letter (incl which house)

Map

What to bring

What to expect

** Welcome folder/bag includes

Welcome letter/Booklet including

Week planner

Small groups (adults & kids)

Badge, sweeties, bookmark